## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Absence of Insights for the Relationship Between Student's Economic Background, Academic Performance, Competence & Expected Salary
PROJECT SPONSOR | Tushar Topale – Director, CC-GAC Foundation
PROJECT MANAGER | Harshada Topale – Director, Cloud Counselage Pvt. Ltd.
EXPECTED START DATE | 15-Jun-2026
EXPECTED COMPLETION DATE | 30-Jul-2026
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.)
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Over 70% of resumes are rejected in initial screening due to lack of relevant skills and competitive positioning. Cloud Counselage organises events to upskill students, but lacks data-driven insights into what factors — family income, GPA, Python experience — actually drive salary expectations and employability. This project fills that gap by analysing real student data to help optimise event design, outreach channels, and mentoring focus areas.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Performance Goal: Successfully complete analysis for all 17 business questions using Python (Pandas, NumPy and Matplotlib) and generate actionable business insights. Time Goal: Complete analysis and all deliverables within the 240-hour GPI internship duration, by 30-Jul-2026. Resource Goal: Individually executed project using Python, VS Code, Microsoft Excel, and open-source libraries (pandas, NumPy, matplotlib) — zero project cost.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Python Submission Document (Word) — 17 analytical questions answered with code and conclusions 2. Project Charter (this document) 3. Software Requirement Specifications (SRS) 4. Requirement Elicitation Questionnaire 5. Work Breakdown Structure (WBS) PPT 6. Project Schedule (Gantt Chart) 7. RAID Log 8. Lessons Learnt Log 9. Project Report
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | - Exploratory data analysis on the provided dataset (Power_BI_Updated_Data_analyst_Data.xlsx) - Answering all 16 prescribed questions using Python - Identifying relationships between family income, CGPA, Python experience, and expected salary - City-wise and college-wise student distribution analysis - Event participation and promotion channel analysis
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | - Building a predictive machine learning model - Dashboard or Power BI visualisation (beyond matplotlib charts) - Primary data collection or surveys - Analysis of students outside the provided dataset
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Intern (Individual Project): Swayam Ballal — Data Analytics Intern, VIT Mumbai
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | - Dataset: Power_BI_Updated_Data_analyst_Data.xlsx (provided by Cloud Counselage) - Tools: Python 3.x, pandas, matplotlib, openpyxl, MS Word - Guidance: Project Manager (Harshada Topale), Domain Lead
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N.A. — All tools are open-source. No financial cost incurred.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd. / Industry Academia Community (IAC)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | 1. Cloud Counselage Pvt. Ltd. — Primary client and programme organiser 2. CC-GAC Foundation — Co-organiser and beneficiary of insights 3. Harshada Topale — Project Manager 4. Tushar Topale — Project Sponsor 5. Swayam Ballal — Intern / Data Analyst
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd. and CC-GAC Foundation
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Data quality issues (missing values, inconsistent entries) may affect analysis accuracy. 2. Ambiguity in categorical variables (e.g., Family Income ranges) may limit numerical analysis. 3. Time constraints of the 240-hour internship duration may limit depth of analysis.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. The dataset provided is accurate and representative of the actual student cohort. 2. Each row represents one unique event registration (not one unique student). 3. Family Income is a self-reported categorical variable. 4. The Quantity column value of 1 for all rows is intentional.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. Analysis must be done using Python only (as per submission format). 2. Project is individual — no team collaboration allowed. 3. Deliverables must be submitted within the 240-hour GPI internship duration.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 06-17-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 06-20-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 06-25-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 07-10-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 07-20-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after submitting the final Python submission document") | 07-28-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 07-30-2026